## Sheet1
Timeline |  | Specs (goals) | Project design | Implementation
10.04.2019 | Project Specifications/Requirements | clarify project goals | Software Design and Architecture | hard layout and design
17.04.2019 | Project design | create timeline (milestones) | Hardware Design, Layout and Architecture | soft architecture
24.04.2019 |  | create Specification Document | Design UI and UX elements (Basic) | soft implementation (see Functional Requiremens document)
08.05.2019 | Implementation + MVP (Beta) | create Functional Requiremens document | Design feature UI and UX elements (ex. Virtual keyboard) | hard implementation (see Functional Requiremens document)
15.05.2019 | Testing (Automated + Manual) | create Non-Functional Requiremens document* |  | create MVP (Beta product)
22.05.2019 | Bugfixing + Improvements
29.05.2019 | Release Candidate
05.06.2019 | Release*
|  | Testing (Automated + Manual) | Bugfixing + Improvements | RELEASE DoD (Definition of Done)
|  | create and run unit tests | fix any issue found on testing | hardware is running
|  | create and run integration tests |  | software is running
|  | create and run validation tests |  | software responds to hardware commands
|  | run non-functional tests (see Non-Functional Requiremens document) |  | all FR and NFR are implemented
|  | find and report issues |  | all features are implemented
HW Components
ESP8266
BUZZER
2x BUTTON
JOYSTICK
2.8" SPI LCD DISPLAY
12x18 cm PROTO BOARD
2x 2N2222 TRANSISTORS